Development Plan

FIXIT — Local Service Booking Platform | Version 1.0

# 1. Development Objective

Turn the PRD, SRS, architecture, and UI/UX specification into a controlled implementation plan. The goal is to deliver the FIXIT MVP without breaking already-working functionality or introducing unnecessary infrastructure.

# 2. Priority Model

| Priority | Meaning |
| --- | --- |
| P0 | Required for core MVP and release. |
| P1 | Important supporting functionality for a complete product. |
| P2 | Post-MVP improvement; do not block MVP release. |

# 3. Milestones

| Milestone | Name | Deliverables | Priority |
| --- | --- | --- | --- |
| M0 | Project baseline | Repository, environment templates, scripts, coding conventions, health check | P0 |
| M1 | Authentication & roles | Customer/provider/admin auth and authorization | P0 |
| M2 | Core catalog & provider | Services, profiles, provider management | P0 |
| M3 | Booking engine | Availability, booking creation, state machine, conflict handling | P0 |
| M4 | Service lifecycle | Confirmation, OTP, service start/completion, timeline | P0 |
| M5 | Trust & engagement | Reviews, ratings, notifications | P0 |
| M6 | Location & discovery | Maps, provider location, radius, nearby search | P0 |
| M7 | Payment & admin | Demo payment flow and admin modules | P0 |
| M8 | UI polish | Stitch-informed professional UI implementation and responsive QA | P1 |
| M9 | Release | Regression, production configuration, deployment, smoke test, documentation | P0 |

# 4. Recommended Implementation Order

Audit the existing repository before modifying it.

Confirm environment variables and local development commands.

Confirm authentication and role middleware.

Confirm database models and indexes.

Implement/verify service catalog APIs and screens.

Implement/verify provider profile and discovery.

Implement/verify availability and booking rules.

Implement/verify the booking state machine.

Implement/verify OTP and service completion.

Implement/verify notifications and reviews.

Implement/verify geolocation and map workflows.

Implement/verify demo payment workflow.

Implement/verify admin dashboard and RBAC.

Apply the Stitch UI/UX system without changing API contracts unnecessarily.

Run automated tests, browser QA, responsive QA, and production smoke tests.

Deploy frontend/backend/database and update documentation.

# 5. Dependencies

Authentication must exist before protected booking/provider/admin features.

Provider/service data must exist before provider discovery and booking.

Availability must exist before reliable booking scheduling.

Booking state machine must exist before OTP, completion, notifications, and payment sequencing.

Completed-service rules must exist before reviews.

Provider location/indexes must exist before nearby search.

Production API URL must be configured before full frontend production smoke testing.

# 6. Testing Plan

| Test Layer | Coverage |
| --- | --- |
| Unit | Pure utilities, validation, and isolated business functions where practical. |
| API/Integration | Authentication, authorization, services, providers, bookings, OTP, reviews, notifications, payments, admin. |
| Regression | Re-run previously passing suites after changes. |
| Browser QA | Critical customer/provider/admin workflows in a real browser. |
| Responsive QA | 375, 390, 768, 1024, 1366, 1920 widths. |
| Security QA | Unauthorized routes, role boundaries, ownership, secret exposure, invalid state transitions. |
| Production Smoke | Homepage, auth, API connectivity, core booking path, notifications, maps, and admin access. |

# 7. Bug-Fixing Workflow

Reproduce the issue and capture the exact failing step.

Determine whether the problem is frontend, backend, database, deployment, or data-related.

Fix the smallest appropriate layer.

Add or update a regression test when practical.

Run the affected tests.

Run the broader regression suite.

Perform browser QA for user-visible changes.

Commit with a focused message and avoid unrelated changes.

# 8. Definition of Done

Requirement is implemented according to the SRS.

Frontend and backend behavior agree on the API contract.

Authentication/authorization and ownership checks are present where required.

Validation and error handling are implemented.

Loading, empty, error, and success states exist for important UI flows.

Relevant automated tests pass.

Existing regression tests still pass.

Responsive behavior is verified.

No known critical console/network errors remain.

Secrets are not committed.

Documentation is updated.

Production deployment/smoke testing is completed before claiming release readiness.

# 9. MVP Release Checklist

Git repository clean and synchronized.

Environment templates available.

Frontend production build succeeds.

Backend health endpoint succeeds in production.

MongoDB production connection succeeds.

CORS allows the deployed frontend.

Authentication works in production.

Provider discovery works.

Booking lifecycle works.

OTP verification works.

Demo payment works.

Reviews and notifications work.

Maps and nearby provider discovery work.

Admin RBAC works.

Critical browser flows pass.

README and deployment documentation are current.

# 10. Post-MVP Backlog

Real payment gateway integration.

Email/SMS/WhatsApp/push notifications.

Real-time messaging/WebSockets.

Advanced provider matching/recommendations.

More sophisticated analytics.

Provider subscription/billing features.

Advanced scheduling and recurring services.

Additional accessibility and localization work.